## Project_change_requests
Project_change_requests Project Reference Number | Project_change_requests Change Order Date | Project_change_requests Change Order Decrease | Project_change_requests Change Order Reason | Project_change_requests Change Order Increase | Project_change_requests Change Order Status ID | Project_change_requests Change Order Type ID | Project_change_requests Creation Time | Project_change_requests Deletion Time | Project_change_requests Is Deleted | Project_change_requests Last Modification Time | Project_change_requests Other Change Order Type | Project_change_requests Project Reference Number
230000000000 | 2020-12-28 | NULL | Contractor contract extension | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 11:52 | NULL | 0 | NULL | NULL | 230000000000
230000000000 | 2022-02-02 | NULL | Contractor contract extension | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 11:52 | NULL | 0 | NULL | NULL | 230000000000
230000000000 | 2021-06-15 | NULL | Contractor contract extension | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 11:52 | NULL | 0 | NULL | NULL | 230000000000
230000000000 | 2020-06-25 | NULL | Contractor contract extension | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 11:52 | NULL | 0 | NULL | NULL | 230000000000
230000000000 | 2022-07-27 | NULL | Contractor contract extension | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 11:52 | NULL | 0 | NULL | NULL | 230000000000
230000000000 | NULL | NULL | 2023-02-28 | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 11:52 | NULL | 0 | NULL | NULL | 230000000000
230000000000 | 2020-12-28 | NULL | Contractor contract extension | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 10:11 | NULL | 0 | NULL | NULL | 230000000000
230000000000 | 2022-02-02 | NULL | Contractor contract extension | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 10:11 | NULL | 0 | NULL | NULL | 230000000000
230000000000 | 2021-06-15 | NULL | Contractor contract extension | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 10:11 | NULL | 0 | NULL | NULL | 230000000000
230000000000 | 2020-06-25 | NULL | Contractor contract extension | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 10:11 | NULL | 0 | NULL | NULL | 230000000000
230000000000 | 2022-07-27 | NULL | Contractor contract extension | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 10:11 | NULL | 0 | NULL | NULL | 230000000000
230000000000 | 2022-07-27 | NULL | Contractor contract extension | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 10:11 | NULL | 0 | NULL | NULL | 230000000000
231000000000 | 2020-12-28 | NULL | Corona pandemic and lack of liquidity in the annual budget | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 10:25 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-02-01 | NULL | Lack of liquidity in the annual budget | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 10:25 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2023-02-16 | NULL | Lack of liquidity in the annual budget | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 10:25 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-06-14 | NULL | Corona pandemic and lack of liquidity in the annual budget | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 10:25 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-06-25 | NULL | Corona pandemic and lack of liquidity in the annual budget | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 10:25 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-07-26 | NULL | Lack of liquidity in the annual budget | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-07-31 10:25 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-09-29 | 6676.6 | Distribute the air properly and in harmony with the ceiling of the hall | NULL | Approved (after registering the contract on the Accreditation platform) | Other | 2023-07-31 10:25 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-09-29 | 755094.12 | The need for direct lighting units that match the shape of the hall ceiling and achieve financial savings | NULL | Approved (after registering the contract on the Accreditation platform) | Other | 2023-07-31 10:25 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-02-04 | NULL | Corona pandemic | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-06-13 09:50 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-06-13 | NULL | Increase project value by 10% | 8843000 | Approved (after registering the contract on the Accreditation platform) | In addition to the scope of work | 2023-06-13 09:50 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2023-01-09 | NULL | Increase project value by 10% | 702118 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-06-12 11:30 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-09-05 | 0 | Delay in issuing extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-06-12 11:30 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-08-15 | NULL | Increase project value by 10% | 9881250 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-06-19 08:53 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2016-10-16 | NULL | Increase project value by 10% | 37126703 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-06-12 11:02 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2017-07-18 | NULL | Increase project value by 10% | 9492162 | Approved (after registering the contract on the Accreditation platform) | In addition to the scope of work | 2023-06-13 09:28 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-09-01 | 0 | Delay in issuing extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-06-01 09:31 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2023-01-10 | 4275253 | NULL | 4275253 | Approved (after registering the contract on the Accreditation platform) | Other | 2023-06-12 10:51 | NULL | 0 | NULL | Reduction, replacement and creation of items | 231000000000
231000000000 | 2022-12-14 | 9035369 | NULL | 9035369 | Approved (after registering the contract on the Accreditation platform) | Other | 2023-06-12 10:51 | NULL | 0 | NULL | Reducing, replacing, adding and creating items | 231000000000
231000000000 | 2022-12-15 | 9703279 | Cancel, reduce, add and create items | 9703277 | Approved (after registering the contract on the Accreditation platform) | Partial cancellation within the scope of work | 2023-06-12 10:51 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-06-06 | NULL | Increase project value by 10% | 6683887 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-06-12 10:51 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-07-13 | 675490 | Reduction, cancellation, increase and creation of items | 675420 | Approved (after registering the contract on the Accreditation platform) | In addition to the scope of work | 2023-06-12 10:51 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-11-09 | 0 | Delayed extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-22 09:22 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-12-19 | 0 | Delayed extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-22 09:22 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-02-11 | 0 | Delayed extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-22 09:22 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-04-26 | 0 | NULL | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-22 09:22 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-04-07 | 0 | Delayed extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-22 09:22 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-06-27 | 0 | Delayed extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-22 09:22 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-08-16 | 0 | Delayed extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-22 09:22 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-09-15 | 0 | Delayed extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-22 09:22 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-09-25 | 0 | Delayed extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-22 09:22 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2017-10-29 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-16 09:52 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2018-10-08 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-16 09:52 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-12-18 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-16 09:52 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2016-12-21 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-16 09:52 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2018-12-24 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-16 09:52 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-12-03 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-16 09:52 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-02-12 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-16 09:52 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2015-02-18 | NULL | NULL | 3684213.05 | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-16 09:52 | NULL | 0 | NULL | Change project quantities and durations | 231000000000
231000000000 | 2018-02-06 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-16 09:52 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2016-03-02 | 1016663.92 | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-16 09:52 | NULL | 0 | NULL | Change project quantities and durations | 231000000000
231000000000 | 2018-03-27 | NULL | NULL | 17192.88 | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-16 09:52 | NULL | 0 | NULL | Change project quantities and durations | 231000000000
231000000000 | 2019-04-01 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-16 09:52 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-04-14 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-16 09:52 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2015-05-30 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-16 09:52 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2017-05-09 | 1869788.1 | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-16 09:52 | NULL | 0 | NULL | Change project quantities and durations | 231000000000
231000000000 | 2020-06-14 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-16 09:52 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-06-17 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-16 09:52 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2018-07-01 | NULL | NULL | 17364.32 | Approved (after registering the contract on the Accreditation platform) | Other | 2023-05-16 09:52 | NULL | 0 | NULL | Change in project quantities and durations | 231000000000
231000000000 | 2014-08-13 | NULL | NULL | 1709768.2 | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-16 09:52 | NULL | 0 | NULL | Change project quantities | 231000000000
231000000000 | 2017-08-03 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-16 09:52 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-09-16 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-16 09:52 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2016-01-31 | NULL | NULL | 490515.31 | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2016-10-20 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-12-01 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2017-12-17 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-02-17 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-02-24 | NULL | NULL | 498774.01 | Approved (after registering the contract on the Accreditation platform) | Other | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2015-03-26 | NULL | NULL | 3010067.73 | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-03-03 | 559894.46 | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Other | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2017-04-01 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2014-04-03 | NULL | NULL | 4893987.1 | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2016-05-26 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-07-07 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2018-09-12 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-09-12 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2017-09-25 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-09-08 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 09:45 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-10-08 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 11:43 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-12-11 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 11:43 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2017-12-07 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-15 11:43 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-12-08 | NULL | NULL | 610468.81 | Approved (after registering the contract on the Accreditation platform) | Other | 2023-05-15 11:43 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-02-10 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 11:43 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2016-02-22 | 3424852.85 | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-15 11:43 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2015-02-09 | 45500 | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-15 11:43 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2017-04-02 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-15 11:43 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-05-29 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 11:43 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-05-03 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 11:43 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2018-05-30 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-15 11:43 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-05-05 | 4314386.55 | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Other | 2023-05-15 11:43 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2016-07-27 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-15 11:43 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2017-07-27 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-15 11:43 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2018-01-03 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-15 13:16 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-12-21 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 13:16 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-12-26 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 13:16 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-02-01 | NULL | NULL | 3480394.66 | Approved (after registering the contract on the Accreditation platform) | Other | 2023-05-15 13:16 | NULL | 0 | NULL | Project quantity calibration | 231000000000
231000000000 | 2015-03-26 | 75983.31 | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-15 13:16 | NULL | 0 | NULL | Change project quantities | 231000000000
231000000000 | 2017-04-01 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-15 13:16 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-04-09 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 13:16 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-05-16 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 13:16 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-05-25 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 13:16 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-06-19 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 13:16 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2017-08-16 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-15 13:16 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2018-08-08 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-15 13:16 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-08-09 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-15 13:16 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | NULL | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-15 13:16 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2023-02-09 | NULL | Increase project value by 10% | 366529 | Approved (after registering the contract on the Accreditation platform) | In addition to the scope of work | 2023-06-13 09:36 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2023-01-10 | NULL | Increase project value by 10% | 379500 | Approved (after registering the contract on the Accreditation platform) | In addition to the scope of work | 2023-06-14 13:42 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-12-05 | NULL | Increase project value by 10% | 12976461 | Approved (after registering the contract on the Accreditation platform) | In addition to the scope of work | 2023-06-13 09:25 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2023-03-07 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-06-13 09:25 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-11-10 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-16 10:53 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-11-08 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-16 10:53 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-02-26 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-16 10:53 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-03-29 | NULL | NULL | 261348.03 | Approved (after registering the contract on the Accreditation platform) | Other | 2023-05-16 10:53 | NULL | 0 | NULL | Change in project quantities | 231000000000
231000000000 | 2017-04-25 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-16 10:53 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2016-06-02 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-16 10:53 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2018-06-26 | NULL | NULL | 2295918 | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-16 10:53 | NULL | 0 | NULL | Change project quantities and durations | 231000000000
231000000000 | 2022-06-05 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-16 10:53 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2017-06-07 | 8792351.17 | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-16 10:53 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-08-12 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-16 10:53 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-10-13 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-17 13:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2016-11-09 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-17 13:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2017-12-31 | 153079.17 | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-17 13:07 | NULL | 0 | NULL | Change project quantities | 231000000000
231000000000 | 2018-12-06 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-17 13:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-12-09 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-17 13:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2017-03-06 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-17 13:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2018-03-06 | NULL | NULL | 3305839.92 | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-17 13:07 | NULL | 0 | NULL | Change project quantities and durations | 231000000000
231000000000 | 2019-05-14 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-17 13:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2017-05-08 | 2536593.84 | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-17 13:07 | NULL | 0 | NULL | Change project quantities | 231000000000
231000000000 | 2016-06-01 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-17 13:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2018-07-03 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-17 13:07 | NULL | 0 | NULL | Change project quantities and durations | 231000000000
231000000000 | 2017-07-09 | NULL | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Extend the time period | 2023-05-17 13:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-08-15 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-17 13:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-09-14 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-17 13:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-09-06 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-17 13:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-12-08 | 0 | Delayed extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-22 08:18 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-08-09 | 0 | Delayed extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-22 08:18 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-09-27 | 0 | During the period of implementing direct preventive measures to deal with the consequences of the spread of the novel coronavirus (COVID-19) pandemic. | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-22 08:18 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-01-02 | 0 | Delay in issuing extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-17 11:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-11-12 | 0 | Delay in issuing extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-17 11:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-12-26 | 0 | Delayed extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-17 11:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-12-07 | 409799 | NULL | 0 | Approved (after registering the contract on the Accreditation platform) | Other | 2023-05-17 11:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-03-25 | 0 | Create items | 1876128.03 | Approved (after registering the contract on the Accreditation platform) | Other | 2023-05-17 11:07 | NULL | 0 | NULL | more | 231000000000
231000000000 | 2022-04-03 | 0 | Delayed extracts | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-17 11:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2022-06-13 | 0 | Add quantities | 506013.09 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-17 11:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-09-12 | 0 | The period of implementing direct preventive measures to deal with the consequences of the spread of the novel coronavirus (Covid-19) pandemic | 0 | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-17 11:07 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-10-28 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-18 13:13 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-10-29 | NULL | NULL | 116448 | Approved (after registering the contract on the Accreditation platform) | Other | 2023-05-18 13:13 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2021-10-04 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-18 13:13 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2018-12-17 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-18 13:13 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2023-02-13 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-18 13:13 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2019-03-30 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-18 13:13 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2018-05-20 | 984228 | NULL | NULL | Certified (before registering the contract on the Accreditation Platform) | Other | 2023-05-18 13:13 | NULL | 0 | NULL | Change in project quantities | 231000000000
231000000000 | 2021-05-25 | NULL | NULL | 283520 | Approved (after registering the contract on the Accreditation platform) | Other | 2023-05-18 13:13 | NULL | 0 | NULL | Change in project quantities | 231000000000
231000000000 | 2022-06-23 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-18 13:13 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2018-06-25 | NULL | NULL | 250332 | NULL | Other | 2023-05-18 13:13 | NULL | 0 | NULL | Change in project quantities | 231000000000
231000000000 | 2018-07-02 | NULL | NULL | 250704.8 | Approved (after registering the contract on the Accreditation platform) | Other | 2023-05-18 13:13 | NULL | 0 | NULL | Change in project quantities and durations | 231000000000
231000000000 | 2019-08-20 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-18 13:13 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2020-09-13 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-18 13:13 | NULL | 0 | NULL | NULL | 231000000000
231000000000 | 2018-09-16 | NULL | NULL | NULL | Approved (after registering the contract on the Accreditation platform) | Extend the time period | 2023-05-18 13:13 | NULL | 0 | NULL | NULL | 231000000000