## contracts
Contracts ID | Contracts Project Id | Contracts Awarding Date | Contracts Actual Start Date | Contracts Advance Payment Related Project | Contracts Billing Amount | Contracts Business Domain | Contracts Billing Amount Related Project | Contracts Commercial Registration Number | Contracts Contract Name | Contracts Contractor CR Status | Contracts Contractor End Date | Contracts Contractor Name | Contracts Contract Related Project Amount | Contracts Current Progress | Contracts Etimad Reference Number | Contracts Etimad Contract Amount | Contracts Expected Contract Related Project Amount Finish | Contracts Expected End Date | Contracts Expected Start Date | Contracts Final Actual End Date | Contracts Initial Actual End Date | Contracts Is Advanced Payment | Contracts Is Contract Consultation | Contracts Is Contract Migrated By Job | Contracts Is Contract Replacement | Contracts Is Contract Signed | Contracts Is Total Linked | Contracts Measure Progress | Contracts Measure Progress 1 | Contracts Old Current Progress | Contracts Old Outgoing | Contracts Old Planned Progress | Contracts Original End Date | Contracts Working Status | Contracts Unpaid Extracts | Contracts Remaining Amount | Contracts Planned Progress | Contracts Planned End Date | Contracts Outgoing Out Of Etimad Related Project | Contracts Outgoing Out Of Etimad | Contracts Outgoing
08CBD684-2CBC-8FED-2375-3A0B2B7F08F0 | 1E077CDB-1135-BE7C-44D9-3A0B2B7D6250 | 2022-09-08 | 0:00 | 209084 | 522608.56 | restoration | 522608.56 | 1010238249 | Replacing the water and thermal insulation in the Majmaah Sports City | NULL | 2023-03-08 | Al Mashreq Heritage Contracting Company | 2090849.5 | 0 | 221000000000 | 2090849.5 | 2090849.5 | 0:00 | 0:00 | NULL | NULL | 1 | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 100 | 0:00 | 0 | 0 | 884026.05
097DC0AD-BEC6-4413-4FDF-3A0B0D615412 | 9E6D15EE-88C6-06E2-9D07-3A0B0D584032 | 2018-08-01 | 0:00 | 0 | 51972780.47 | Construction | 0 | 2051027134 | Establishing classrooms attached to some university colleges in the governorates | NULL | 2019-07-06 | Khader Trading and Contracting Company | 73496430 | 83 | 190000000000 | 73496430 | 80600554 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 85 | 0:00 | 0 | 0 | 52773071.69
0B4BEE97-6821-98C5-07F9-3A0A821F9308 | DBFD2BCC-D804-4AE8-D0A0-3A0A8219E523 | 2019-05-06 | 0:00 | 0 | 0 | Construction | 0 | 4030173390 | Classrooms for Girls' Urgent Health Colleges - Phase II in Al-Abdiyah | NULL | 2020-07-29 | Tamas Saudi Construction and Development Company Limited | 67468513 | 0 | 221000000000 | 67468513 | 67468513 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 4 | Cost of work done | 0 | 0 | 0 | 0:00 | Current | 0 | 0 | 0 | 0:00 | 0 | 0 | 0
0CD7F5D3-7C2A-40E7-4247-3A0B3575AE25 | 9210D512-80B8-BA32-28CE-3A0B3572537D | 2022-10-03 | 0:00 | 0 | 3036000 | Construction | 0 | 1010196594 | Replacing the umbrellas in the university city | NULL | 2022-12-01 | Ibrahim Hassan Al Ajlan Contracting Company | 3795000 | 100 | 221000000000 | 3795000 | 3795000 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | In progress - preliminary receipt | 0 | 0 | 99 | 0:00 | 0 | 0 | 0
1377564F-54D5-B461-B4D4-3A0B0D32D02C | 3E7E4862-6DEE-E6AB-22FE-3A0B0D2C7E44 | 2018-03-22 | 0:00 | 0 | 54833812.44 | Construction | 0 | 1131013992 | Infrastructure Project Contract No. 5 at the University City | NULL | 2021-02-01 | Mansour Bin Suleiman Al Rawaf and Partner Trading & Contracting Company | 74728018.81 | 100 | 200000000000 | 74728018.81 | 98812500 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | In progress - preliminary receipt | 0 | 0 | 100 | 0:00 | 0 | 98812500 | 54833812.44
1420E736-8110-87BC-785F-3A0B35578138 | 73F1B98F-881E-F190-9A1C-3A0B35538170 | 2022-09-25 | 0:00 | 0 | 0 | Construction | 0 | 1128001366 | Implementation of an electrical room at the university colleges headquarters in Unaizah Governorate | NULL | 2022-12-23 | Al-Azelon Al-Najd Contracting Establishment | 695738.5 | 100 | 221000000000 | 695738.5 | 695738 | NULL | 0:00 | NULL | 0:00 | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Completed - Initial Receipt | 0 | 0 | 100 | 0:00 | 0 | 0 | 0
176342E4-2895-38F4-D68B-3A0B357AD8C1 | 5C813548-E93F-5062-8AA2-3A0B3578E229 | 2022-11-03 | 0:00 | 0 | 0 | Construction | 0 | 1010669881 | Implementation of a parents' lounge at Qassim University | NULL | 2023-04-29 | Sama International Contracting Company | 1530908.75 | 7 | 221000000000 | 1530908.75 | 1530910 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 16 | 0:00 | 0 | 0 | 0
183074F2-A8FB-5FE7-B1A9-3A0B2835CC60 | 8B31953C-E263-6722-A70A-3A0B28335F5C | 2022-08-03 | 0:00 | NULL | 960552.35 | restoration | 960552.35 | 1010131784 | Replacing the water and thermal insulation in King Fahd Sports City in Taif | NULL | 2023-02-03 | Arab Company for Building Support and Rehabilitation Limited | 2811399.25 | 95 | 230000000000 | 2811399.25 | 2811399.25 | 0:00 | 0:00 | NULL | NULL | 0 | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 100 | 0:00 | 0 | 0 | 889432.17
25BBDF8D-76C1-8494-A9DA-3A0AD4953DFE | 84C9D9D1-CF03-4759-CD6C-3A0AD4906ACF | 2019-05-22 | 0:00 | 0 | 29142023.81 | Supply and installation | 0 | 2252004545 | Replacement and modernization works in cooling stations (2/1) and service tunnel in the university campus, Umm Al-Qura University 419185 | NULL | 2020-05-22 | Saudi Air Conditioning, a branch of Abdul Latif Mohammed Al Arfaj & Brothers Holding Company | 34857764.34 | 99 | 201000000000 | 34857764.34 | 34857764.34 | NULL | 0:00 | NULL | 0:00 | NULL | 0 | 0 | 0 | 1 | 1 | 4 | Cost of work done | NULL | 0 | NULL | 0:00 | Completed - Initial Receipt | 0 | 0 | 100 | 0:00 | 0 | 34857764.34 | 29142023.81
2FE45B19-A27F-AD9A-5C79-3A0D5D86F75E | 83666C7D-6F44-06B8-C73E-3A0AEFB51B7B | 2009-02-10 | 0:00 | 45463073.32 | 0 | Construction | 0 | 4030008659 | Implementation of the project of the female students’ headquarters buildings (2) in Al-Abidiyah | NULL | 2013-04-10 | Rabieh Trading and Agriculture Company | 45828262.72 | 91 | 181000000000 | 45828262.72 | 45828262.72 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 4 | Cost of work done | NULL | NULL | NULL | 0:00 | drawn | 0 | 0 | 100 | 0:00 | 243900963.8 | 243900963.8 | 0
32F93324-9823-2C38-CE2D-3A0B2BA390F1 | F30001A0-804C-0388-1318-3A0B2B89E23A | 2019-01-01 | 0:00 | 132227 | 0 | Supply and installation | 0 | 1010279541 | Replacing the lighting of the main stadium of Al-Batin Club in Hafar Al-Batin | NULL | 2019-06-01 | Energy Lights Contracting Est. | 1322276 | 100 | 191000000000 | 1322276 | 1322276 | 0:00 | 0:00 | NULL | NULL | 1 | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | In progress - preliminary receipt | 0 | 0 | 100 | 0:00 | 0 | 0 | 1322275.5
3B0FC980-D4E2-DB01-3208-3A0B27EE659E | 55711B12-CF5E-6347-6F12-3A0B27E53890 | 2022-09-05 | 0:00 | 194653 | 346725 | Other | 346725 | 1010735699 | Replacing the secondary stadium floor with natural grass in Majmaah Sports City in Majmaah | NULL | 2023-02-15 | Rawshn First Contracting Company is a one-person company. | 2063031.31 | 0 | 221000000000 | 2063031.31 | 1946536 | 0:00 | 0:00 | NULL | NULL | 1 | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 100 | 0:00 | 0 | 0 | 1716306
3B5AEBBF-0F3E-9A3F-B671-3A0B407AE426 | 27C65D57-E956-38E2-623D-3A0B4077019B | 2017-12-07 | 0:00 | 0 | 2485118.28 | Construction | 0 | 1010235877 | Completion of the construction of the e-training building project at the Technical College in Medina | NULL | 2021-09-10 | Sanabel Al-Asima Contracting Company | 4955361.77 | 57 | 181000000000 | 4955361.77 | 4840897.6 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 5 | Invoiced cost | NULL | 0 | NULL | 0:00 | Total shutdown | 0 | 0 | 100 | 0:00 | 0 | 5170326.84 | 2505402.71
3FAF2E58-708A-BF87-1C99-3A0B2B804CD8 | D5F9F4FE-F3CE-8E6B-885A-3A0B2B6F02CF | 2012-04-14 | 0:00 | 8399597.59 | 14998058.25 | Construction | 0 | 2050022661 | Establishment of the Technical College for Girls in Taif | NULL | 2021-07-04 | Al Waseet Architectural Company Limited is a one-person company. | 28968264.62 | 90 | 181000000000 | 28968264.62 | 92329710.63 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 5 | Invoiced cost | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 100 | 0:00 | 0 | 83996260.94 | 16387764.95
405A545D-E5D4-8AD2-95D5-3A0B0CF0F40E | C3606764-36EC-BE0D-3E9E-3A0B0CD78676 | 2019-04-23 | 0:00 | 0 | 128412556.8 | Construction | 0 | 1010009593 | Awarding the remaining works in the contract to build and equip the conference center at Qassim University | NULL | 2021-05-23 | Al Mansouria General Contracting Company | 134386920.1 | 77 | 200000000000 | 134386920.1 | 210000000 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 85 | 0:00 | 0 | 199506832.8 | 118875427
4F937E15-FD7C-3F26-013B-3A0B3104C6CF | BB548A09-5821-5D6C-4545-3A0B30F6C723 | 2014-02-25 | 0:00 | 8160575.6 | 14019294.12 | Construction | 0 | 2050040480 | Establishment of the Technical College for Boys in Buqayq | NULL | 2016-07-16 | Jas International Contracting Company | 56140648.42 | 39.2 | 181000000000 | 56140648.42 | 85010167.34 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 5 | Invoiced cost | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 100 | 0:00 | 0 | 85606261.31 | 14875911.96
4FE5D685-3239-ED9E-8C7F-3A0B1BF161DA | C2C61709-0D2D-14C1-5E19-3A0B1BE2A934 | 2012-01-02 | 0:00 | 11976313.7 | 7742128.01 | Construction | 0 | 1010011949 | Replacing the Secondary Institute of Architecture and Construction in Riyadh | NULL | 2020-02-05 | Tharb Trading & Contracting Company | 25451387.89 | 71 | 181000000000 | 25451387.89 | 62067404.93 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 5 | Invoiced cost | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 100 | 0:00 | 0 | 59881568.5 | 7742128.01
5729988A-4C62-6D1F-1417-3A0B356E8D19 | FFBDB554-CA95-BACE-3DB1-3A0B356BB020 | 2022-11-03 | 0:00 | 0 | 2447815.01 | Construction | 0 | 1128001788 | Implementation of irrigation networks, sidewalks and lighting in the sites of female colleges at Qassim University and its branches | NULL | 2023-07-03 | Abdulmalik Sulaiman Bin Saif Contracting Establishment | 3665298.4 | 45 | 221000000000 | 3665298.4 | 3665299 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 55 | 0:00 | 0 | 0 | 593874.75
59C45DC1-CFA3-D7E5-E9D6-3A0B308371F5 | 8C27EE80-2D3B-1885-CC21-3A0B307AE5E6 | 2014-03-26 | 0:00 | 18597446.32 | 31854406.08 | Construction | 0 | 2051003250 | Establishment of the Technical College for Girls in Sharurah | NULL | 2016-08-13 | Ali Hussein Al-Yami and Partner Company for Trade and Contracting | 44093204.99 | 87.45 | 181000000000 | 44093204.99 | 87232561.02 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 5 | Invoiced cost | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 100 | 0:00 | 0 | 95483302.69 | 31733024.69
603A877F-A0EB-0D93-A5CA-3A0B35D54E9E | 2287E058-C911-F6E9-6521-3A0B35CC5C8A | 2014-07-18 | 0:00 | 9939088.09 | 5096278.03 | Construction | 0 | 1010145283 | Establishing housing for female trainers at the Technical College for Girls in Al-Ahsa (Colleges of Excellence) | NULL | 2016-05-28 | Rukn Al Qusour Contracting Establishment, owned by Hamad Al Sheikh* | 13801257.23 | 81 | 181000000000 | 13801257.23 | 47986390.7 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 5 | Invoiced cost | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 100 | 0:00 | 0 | 50385710.23 | 5096278.03
6256A85C-77DE-8D10-41C8-3A0BF395DC6F | 89625A54-6361-8A68-1B1E-3A0B07DB5784 | 2019-10-03 | 0:00 | 0 | 1006804.37 | Construction | 1006804.37 | 1010171914 | Implementation of the conference hall works project at the institute’s branch in Makkah Al-Mukarramah | NULL | 2020-03-28 | First Gulf Contracting and Contracting Company | 21664194.48 | 24 | 191000000000 | 21664194.48 | 21664194.48 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 5 | Invoiced cost | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 50 | 0:00 | 0 | 0 | 4666918.61
68195CD2-97C4-0605-E091-3A0B12757212 | 2CDB805A-F5EE-B42B-5EB3-3A0B1272494B | 2019-04-25 | 0:00 | 0 | 66838874.39 | Construction | 0 | 1131032608 | Implementation of supplementary works for the College of Medicine, Contract (B), at Qassim University | NULL | 2021-04-14 | Maten Trading & Contracting Co. Ltd. | 66838874.39 | 100 | 191000000000 | 66838874.39 | 66838874 | NULL | 0:00 | NULL | 0:00 | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Completed - Initial Receipt | 0 | 0 | 100 | 0:00 | 0 | 0 | 56759217.21
6DBAE893-4F6C-5729-30DB-3A0B3AA819ED | 08654958-92CA-ECBF-8286-3A0B3A985579 | 2019-07-31 | 0:00 | 0 | 2962836.81 | Construction | 0 | 4030010046 | Completion of the construction of the housing of the College of Training of Female Trainers in Jeddah | NULL | 2021-04-28 | Our Home Construction Company | 9779762.61 | 41 | 191000000000 | 9779762.61 | 8994969.27 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 4 | Cost of work done | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 100 | 0:00 | 0 | 0 | 2962836.81
77CBB14B-591B-FF9B-3470-3A0AD4030033 | 6337290F-B424-7CA2-0FD3-3A0AD3F57ED2 | 2019-12-30 | 0:00 | 0 | 1034553.28 | Construction | 0 | 4030215478 | Establishment of a VIP lounge attached to King Abdulaziz Hall 419093 | NULL | 2020-06-27 | Roya Administrative Company for Commercial Services | 4159533 | 27 | 200000000000 | 4159533 | 4159533 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 4 | Cost of work done | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 100 | 0:00 | 0 | 0 | 1034553.28
7C1E036B-656F-9232-CC88-3A0B356472C9 | 22C3290A-6779-F439-B876-3A0B355D693F | 2022-08-17 | 0:00 | 0 | 0 | Construction | 0 | 1010278646 | Tender for implementing modifications to the external electrical room in Al-Rass and the medium voltage cable clinics | NULL | 2023-08-06 | Electromechanical Projects Contracting Establishment | 281493.55 | 100 | 221000000000 | 281493.55 | 281493 | NULL | 0:00 | NULL | 0:00 | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Completed - Initial Receipt | 0 | 0 | 99 | 0:00 | 0 | 0 | 0
7CB04B98-7B2A-95C4-E834-3A0B281921D6 | A63E247B-20B2-0947-03FB-3A0B2816BC55 | 2022-10-04 | 0:00 | 177219 | 0 | restoration | 0 | 1010131784 | Replacing the water and thermal insulation in King Faisal Sports City in Jazan | NULL | 2023-04-04 | Arab Company for Building Support and Rehabilitation Limited | 1772190.25 | 75 | 221000000000 | 1772190.25 | 1772190.25 | 0:00 | 0:00 | NULL | NULL | 1 | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 90 | 0:00 | 0 | 0 | 1157166.8
847E92A4-F953-61A6-8972-3A0B0D4BCD12 | D431094C-8DBD-F5F7-0817-3A0B0D4790C1 | 2020-05-05 | 0:00 | 18984326 | 0 | Construction | 0 | 1016812982 | 10% increase in the contract to establish the infrastructure for the general website for female students with me | NULL | 2020-06-04 | Rawaf Suleiman Abdullah Al Rawaf | 9492163.05 | 78 | 211000000000 | 9492163.05 | 104413766 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 79 | 0:00 | 0 | 9492163.05 | 0
8989211A-F27F-E971-D51A-3A0B3587CC76 | 55B64E26-AC35-E8B6-6DF4-3A0B35843996 | 2018-11-21 | 0:00 | 25952924 | 59872840.1 | Construction | 0 | 1010034600 | Establishment of the College of Medicine, Medical and Applied Sciences at the University Colleges Complex in Unaizah Governorate | NULL | 2022-05-04 | Safari Company is a closed joint stock company. | 82749837.9 | 92 | 181000000000 | 82749837.9 | 140273996 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | In progress - preliminary receipt | 0 | 0 | 100 | 0:00 | 0 | 139764620 | 64759054.39
89B97D02-7CE1-3030-01B8-3A0AD362EB98 | 903A9288-1990-3FE4-BE93-3A0A87E4EF90 | 2018-10-16 | 0:00 | 0 | 0 | Construction | 0 | 3350018863 | Supply and installation of a scoreboard for the main stadium of Al-Ansar Sports Club in Medina | NULL | 2019-06-16 | Al-Taraheeb Contracting Establishment | 799150 | 50 | 181000000000 | 799150 | 799147 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 50 | 0:00 | 0 | 0 | 0
8AC9CDEF-CD13-2E50-C8CF-3A0BF3B06EF3 | 0954BD1B-3DDC-FBD1-C59B-3A0A87617506 | 2019-09-30 | 0:00 | 0 | 0 | supervision | 0 | 1010322156 | Supervising the work of the conference hall at the Women's Institute branch in Riyadh | NULL | 2020-03-25 | Saudi Consulting Services Company for Engineering Consultations | 2082024 | 89 | 191000000000 | 2082024 | 2082024 | 0:00 | 0:00 | NULL | NULL | NULL | 1 | 0 | 0 | 1 | 1 | 5 | Invoiced cost | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 95 | 0:00 | 0 | 0 | 1861145.81
8BB07733-5D12-F556-6B09-3A0B1241E3DD | 2CD6954D-3614-17F7-21DF-3A0B122F6B5C | 2022-06-18 | 0:00 | 0 | 708500 | Supply and installation | 0 | 4030168691 | Garden maintenance in Adham | NULL | 2023-06-18 | Al-Raed Trusted General Contracting Establishment | 1515642.5 | 68 | 221000000000 | 1515642.5 | 1515642 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 75 | 0:00 | 0 | 0 | 708500
8DB5D431-C9F5-4529-CF46-3A0B0D40572C | D9D1BEDA-3A81-DD44-C2F6-3A0B0D3C4BC1 | 2011-08-10 | 0:00 | 105835815 | 16904412.3 | Construction | 0 | 2051030201 | Establishing colleges and health laboratories for students at the university | NULL | 2014-01-26 | Rakan Trading and Contracting Company | 31874695.7 | 66 | 200000000000 | 31874695.7 | 616687498 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 68 | 0:00 | 0 | 129500000 | 16904412.3
9695F881-7D86-F4ED-3172-3A0A822A3EE4 | 440E9CF7-E257-1FA1-5A0A-3A0A822780AC | 2019-08-21 | 0:00 | 0 | 0 | Construction | 0 | 4030173390 | Construction of the Central Printing Press Building - Umm Al-Qura University in Makkah Al-Mukarramah | NULL | 2020-08-20 | Tamas Saudi Construction and Development Company Limited | 20159692.05 | 0 | 191000000000 | 20159692.05 | 20159692.05 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 4 | Cost of work done | 0 | 0 | 0 | 0:00 | Current | 0 | 0 | 0 | 0:00 | 0 | 0 | 0
9C40965B-A0B2-067F-150D-3A0BF3A1453F | FBD85B95-9F3A-CFE5-06EC-3A0AD406A937 | 2019-09-30 | 0:00 | 0 | 0 | supervision | 0 | 1010322156 | Supervising the work of the conference hall at the institute’s branch in Makkah Al-Mukarramah | NULL | 2020-03-25 | Saudi Consulting Services Company for Engineering Consultations | 2095632 | 88 | 191000000000 | 2095632 | 2095632 | 0:00 | 0:00 | NULL | NULL | NULL | 1 | 0 | 0 | 1 | 1 | 5 | Invoiced cost | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 90 | 0:00 | 0 | 0 | 1849599.68
A06E812A-DE89-8607-B8DD-3A0B28288D8F | 6986A9ED-A08B-3211-14E1-3A0B28245042 | 2022-08-18 | 0:00 | 119766 | 0 | restoration | 0 | 1010144692 | Replacing the outdoor playground flooring at King Faisal Sports City in Jazan | NULL | 2023-03-18 | Saeed Ahmed Bahamda Contracting Company | 1197667.5 | 0 | 221000000000 | 1197667.5 | 1197667.5 | 0:00 | 0:00 | NULL | NULL | 1 | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 100 | 0:00 | 0 | 0 | 1197667.5
A172DADD-6F25-154C-24FF-3A0B0D166A51 | CDB042B5-ADCC-2588-3DE2-3A0B0D0C2735 | 2019-02-10 | 0:00 | 0 | 7284191.59 | Construction | 0 | 1010186040 | Completion of the second phase of the veterinary laboratory buildings | NULL | 2019-12-04 | Aja Mountains Building Company Limited | 7723317.84 | 99 | 200000000000 | 7723317.84 | 7021198 | NULL | 0:00 | NULL | 0:00 | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Completed - Initial Receipt | 0 | 0 | 100 | 0:00 | 0 | 7021198.04 | 6839101.88
A332D396-948B-8C86-4F9C-3A0B0C647472 | B1300A98-06DD-F3E0-3BEB-3A0B0C5D8504 | 2019-10-28 | 0:00 | 0 | 3444479.53 | Supply and installation | 0 | 4030188853 | Rehabilitation of streets and lighting in Adham and Wafar | NULL | 2021-06-04 | Western Projects Trading & Contracting Company | 3600142.09 | 98 | 210000000000 | 3600142.09 | 3600142.09 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | In progress - preliminary receipt | 0 | 0 | 98 | 0:00 | 0 | 4499999.18 | 3444479.53
AAD3F7A0-2C0A-61A1-F416-3A0B317659AB | 1658D693-92EF-08AE-0F7E-3A0B31717053 | 2022-10-25 | 0:00 | 3213962.5 | 404225 | Supply and installation | 0 | 4030237556 | Maintenance of lighting poles in Adham | NULL | 2025-10-25 | Union Dominance General Contracting Establishment | 3213962.5 | 10 | 221000000000 | 3213962.5 | 3213962.5 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 15 | 0:00 | 0 | 0 | 0
ABED24C8-EEDF-3D75-AE85-3A0B1BC9AB26 | 14E7CDFF-69CC-B3BC-E31A-3A0B1BBD5E77 | 2022-10-25 | 0:00 | 1645937 | 0 | restoration | 0 | 4601002260 | Maintenance of municipal buildings and facilities in Adham | NULL | 2025-10-25 | Osman Khairallah Hamad Al Zahrani Foundation | 1645937 | 2.75 | 221000000000 | 1645937.5 | 1645937 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 0 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 4 | 0:00 | 0 | 0 | 0
B03B8672-3E8D-F386-DF72-3A108A2138BA | 34909C50-F238-2CB3-DA0C-3A0B357DB7C9 | 2022-11-02 | 0:00 | NULL | 0 | Other | 0 | 1134000719 | Preparing the general site and parking lots for female students’ colleges at Qassim University and its branches | NULL | 2023-11-22 | Bandar and Khaled Mohammed Al-Mazid Trading and Contracting Company | 15823228.35 | 44 | 221000000000 | 15823228.35 | 14384765 | 0:00 | 0:00 | NULL | NULL | 0 | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 54 | 0:00 | 0 | 0 | 3132900.27
BE87888B-EAC5-FBD9-AD9B-3A0B3AC54D42 | 9CF671DE-1C61-9B07-5BC7-3A0B3ABEDD2A | 2019-12-15 | 0:00 | 0 | 11566242.45 | Construction | 0 | 1116006476 | Completion of construction of housing for trainers and trainees for the General Motors program in Jeddah | NULL | 2020-09-10 | Construction Forum Company | 20228885.05 | 53 | 210000000000 | 20228885.05 | 22201226.71 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 4 | Cost of work done | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 81 | 0:00 | 0 | 20228885.05 | 9447860.91
C2DE8501-9345-065E-13A6-3A09F6EDA50B | 080E6554-FAA2-D0F4-17AA-3A09F6E7090D | 2022-11-02 | 0:00 | NULL | 0 | Supply and installation | 0 | 1010177619 | Supply and installation of concrete barriers for high-risk entrances and wells and historical wells in the reserve | NULL | 2023-02-02 | Rawae Baladi Co., Ltd. | 1302490 | 97 | 221000000000 | 1302490 | 1302490 | 0:00 | 0:00 | NULL | NULL | 0 | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | 0 | 0 | 0 | 0:00 | Current | 0 | 0 | 99 | 0:00 | 0 | 0 | 575402.5
CBCFB691-C852-A3C2-9E56-3A0B542C2A5C | AB10CCB2-41EE-A22E-120C-3A0B16F1952F | 2017-05-15 | 0:00 | 0 | 1687771.27 | Construction | 0 | 4030219467 | Completion of the construction of the Secondary Industrial Institute in Tanuma | NULL | 2018-03-11 | Al Nafooz Pioneering General Contracting Establishment | 3145280.25 | 53 | 190000000000 | 3145280.25 | 3145279 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 4 | Cost of work done | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 100 | 0:00 | 0 | 0 | 1687771.27
D622682E-4F41-F328-B3B2-3A0B30A0B7D3 | F2FFBEE4-9C04-D9EE-1BE7-3A0B309C3C8F | 2022-01-13 | 0:00 | 7258.8 | 0 | restoration | 0 | 1010351290 | Additional parking spaces at the office of His Highness the Minister of Sports | NULL | 2022-01-23 | Al-Adoud Contracting Company is a one-person company. | 72588 | 100 | 221000000000 | 72588 | 72577 | NULL | 0:00 | NULL | 0:00 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Completed - Initial Receipt | 0 | 0 | 100 | 0:00 | 0 | 0 | 72588
DAAF1F96-DEFF-6634-4F42-3A0B28057569 | 0E7CB1C5-72EA-7FA1-8582-3A0B2802485D | 2022-08-11 | 0:00 | 348271 | 0 | restoration | 0 | 1010075656 | Replacing insulation at Al-Ahly Club in Jeddah, Al-Wehda Club in Makkah Al-Mukarramah, and Al-Majd Club in Yanbu | NULL | 2023-04-11 | Sakhratain General Contracting Company is a one-person company. | 3482717.5 | 0 | 221000000000 | 3482717.5 | 3482717.5 | 0:00 | 0:00 | NULL | NULL | 1 | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 100 | 0:00 | 0 | 0 | 2082696
DCAC25A4-0123-4A73-46E6-3A0B35AB72B3 | 3C8C12CC-0BA7-0C38-1542-3A0B35A32485 | 2014-10-21 | 0:00 | 6979523.45 | 7362458.77 | Construction | 0 | 1010069654 | Establishing housing for male and female trainers at the Technical College for Boys and the Technical College for Girls in Al-Aflaj | NULL | 2022-02-20 | Fad Contracting and Trading Company, owned by Fahd bin Bakhit bin Saad Al-Saffar and his partner | 14420400.37 | 95 | 181000000000 | 14420400.37 | 63560149.31 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 5 | Invoiced cost | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 100 | 0:00 | 0 | 69795234.45 | 10146778.16
E961F07F-8EB3-824F-41B1-3A0B3AAF09EB | DCBB0B78-652E-2E31-5D39-3A0B0D659AEE | 2014-10-19 | 0:00 | 0 | 169346135.9 | Construction | 0 | 1010009593 | Project to establish a female students' college complex in Buraidah | NULL | 2017-10-03 | Al Mansouria General Contracting Company | 193718345.8 | 100 | 200000000000 | 193718345.8 | 313318000 | NULL | 0:00 | NULL | 0:00 | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Completed - Initial Receipt | 0 | 0 | 100 | 0:00 | 0 | 325349403 | 169346135.9
EF8EAD82-7035-470C-E4AE-3A0B36354861 | 19DF30B0-68D8-05D6-F793-3A0B3630F214 | 2015-06-28 | 0:00 | 0 | 9671282.53 | Construction | 0 | 1116004360 | Completion of the establishment of the College of Tourism and Hotels in Al-Ahsa | NULL | 2016-09-06 | Emaar Al Sharif Contracting Company | 42434810.91 | 38 | 181000000000 | 42434810.91 | 49596610.22 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 5 | Invoiced cost | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 100 | 0:00 | 0 | 52076440.73 | 9671282.53
F22E4E7B-F1B4-CB7C-3EC0-3A0B1C3F1C9F | 1B60904E-E314-CF6E-BCF9-3A0B1C2B3716 | 2019-01-07 | 0:00 | NULL | 0 | restoration | 0 | 1010219205 | Replacing the water and thermal insulation at Al-Ittihad Sports Club in Jeddah | NULL | 2019-05-07 | High Land Contracting Establishment. | 946858 | 100 | 191000000000 | 946858 | 946845 | NULL | 0:00 | 0:00 | 0:00 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Final receipt completed | 0 | 0 | 100 | 0:00 | 0 | 0 | 743243
F8FF83C7-6D0B-9080-56E2-3A0B1148BAF3 | 362ECE70-5959-8DFB-C41C-3A0B112F7427 | 2022-03-12 | 0:00 | 0 | 1138500 | restoration | 0 | 4030796312 | Road maintenance in Adham | NULL | 2023-03-12 | Manahi Bajad Manahi Al-Gharmool Al-Baqmi General Contracting Establishment | 1360450 | 85 | 220000000000 | 1360450 | 1360450 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 90 | 0:00 | 0 | 0 | 1138500
F9429BB8-A5C6-A06C-A8E0-3A0AD489B9DB | 354E0DDE-298A-D962-6ED5-3A0AD4875B2B | 2022-11-22 | 0:00 | 0 | 0 | restoration | 0 | 5950004973 | Rehabilitation and upgrading of buildings and facilities at Umm Al-Qura University in Al-Abdiyah and branches in Makkah Al-Mukarramah and Al-Jumum | NULL | 2023-05-18 | Al Fanary Contracting Company is a one-person company. | 3724561.35 | 0 | 230000000000 | 3724561.35 | 3724561.35 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 4 | Cost of work done | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 1 | 0:00 | 0 | 0 | 0
FF00CB7F-6596-D90B-F467-3A0B11FA0361 | ADA5268F-CCFC-CAE6-BC95-3A0B1172625B | 2022-04-01 | 0:00 | 0 | 1276500 | Supply and installation | 0 | 4030796312 | Sidewalk maintenance in Adham | NULL | 2023-03-21 | Manahi Bajad Manahi Al-Gharmool Al-Baqmi General Contracting Establishment | 1741100 | 74 | 220000000000 | 1741100 | 1741100 | 0:00 | 0:00 | NULL | NULL | NULL | 0 | 0 | 0 | 1 | 1 | 1 | Quantities installed | NULL | 0 | NULL | 0:00 | Current | 0 | 0 | 80 | 0:00 | 0 | 0 | 1276500